## Sheet1
PROJECT MANAGEMENT LOG
Project Title |  | SPC Official Website |  |  |  | Start Date |  |  | 2018-11-15
Log Number |  | 1 |  |  |  | Expected End Date
Date Entered | Inform Problem Risk Decision | Description | Project Impact | Action/Resolution | by |  | Expected Date | Priority | Date to Review | Progess Report | Closure Report | Remarks
2019-10-07 | Create | Prompt message on opening the web page | 3 | Inserting prompt message before loading the main page | Hex |  | 2019-09-30 | 1
2019-10-08 | Continuing | Designing and disabling click until aggreeing the terms and conditions | 2 | Putting the prompt message using modal and jQuery to prompt when the window starts | Hex |  | 2019-10-01 | 1
2019-10-09 | Redesign | Designing the modal for view all news | 3 | Redesigning the modals to scroll view | Hex |  | 2019-10-02 | 1
2019-10-10 | Create | Creating new section of building forms | 3 | Inserting the button section for the building and engineering forms | Hex |  | 2019-10-03 | 1
2019-10-11 | Create | Merging the project code of Marco and mine | 2 | Merging the project files on git hub | Hex |  | 2019-10-04 | 1
2019-10-12 | Data Cleansing | Data organizing and preparing database for upload | 2 | Creating tables for the database of the admin panel for uploading | Hex |  | 2019-10-05 | 1
I,We have agreed on the above IPRD & resolution date: |  |  | Conforme for Discussed IPRD and Resolution |  |  | Action/Resolution taken was checked & accepted: |  |  |  |  | Final Remarks:
IT Personnel/Processor |  |  | Name and Signature of Conforme |  |  | Name and Signature of Acceptance